## All Projects
New South Wales Projects
Project Details - Eurobodalla Southern Storage Announced - 2021 Funding Allocated - $51.2 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2018
2. Final Business case | 2018 | 2021
3. Planning and Pre-Construction Activities | 2021 | Early 2022
4. Construction | 2022-01-01 | Mid-2025
Project Details - Nyngan to Cobar Pipeline - Stage 1 Announced - 2022 Funding Allocated - $22.75 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2020 | 2024
2. Final Business case | 2020 | Mid-2022
3. Planning and Pre-Construction Activities | 2022 | 2025
4. Construction | Mid-2025 | Late 2026
Project Details - Yass Water Security Treatment Plant Upgrade Announced 2024 Funding Allocated - $18.1 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | TBD | TBD
2. Final Business case | TBD | TBD
3. Planning and Pre-Construction Activities | TBD | TBD
4. Construction | Early 2027 | Late 2028
Completed Projects | Funding Provided | Completion Date
1. New Dungowan Pipeline - Stage 1 | $27.5 million | 2023-08-01
2. Wyangala Water Treatment Plant. | $2.8 million | 2024-04-01
Victoria Projects
Project Details - Western Irrigation Network Announced - 2020 Funding Allocated - $48.1 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2025
2. Final Business case | 2018 | 2019
3. Planning and Pre-Construction Activities | 2019 | Mid-2020
4. Construction | 2020-12-01 | Late 2025
Project Details - Western Port Recycled Water Scheme - Stage 1 Announced - 2024 Funding Allocated - $46.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | TBD | TBD
2. Final Business case | Late 2021 | 2023-12-01
3. Planning and Pre-Construction Activities | TBC | TBC
4. Construction | Late 2025 | Late 2029
Project Details - East Grampians Water Supply Project Announced - 2019 Funding Allocated - $32.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2024
2. Final Business case | 2018 | 2019
3. Planning and Pre-Construction Activities | 2019 | Mid-2020
4. Construction | 2024-04-01 | Early 2026
Project Details - Quality Water for Wannon Announced - 2023 Funding Allocated - $26.1 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | Mid-2023 | 2029
2. Final Business case | 2019 | 2022
3. Planning and Pre-Construction Activities | Mid-2023 | Late 2028
4. Construction | Mid-2025 | Mid-2029
Project Details - Recycled Water on the Bellarine Announced - 2021 Funding Allocated - $5.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2024
2. Final Business case | N/A | Complete
3. Planning and Pre-Construction Activities | 2021 | Late 2023
4. Construction | 2024-12-01 | 2026
Completed Projects | Funding Provided | Completion Date
1. Sunraysia Modernisation Project 2 | $3.0 million | 2019-10-01
2. South West Loddon Rural Water Supply Project | $20.0 million | 2020-04-01
3. Macalister Irrigation District Modernisation Phase 1B | $20.0 million | 2020-11-01
4. Mitiamo and District Reticulated Water Supply Project | $14.5 million | 2021-04-01
5. Macalister Irrigation District Modernisation Phase 2 | $31.3 million | 2024-09-01
6. Werribee Irrigation District Modernisation (Stage 4 & 5) | $11.0 million | 2024-12-01
Queensland Projects
Project Details - Paradise Dam Improvement Announced - 2022 Funding Allocated - $600.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2019 | TBD
2. Final Business case | 2019 | Early 2026
3. Planning and Pre-Construction Activities | 2020 | TBD
4. Construction | TBD | TBD
Project Details - Hughenden Irrigation Scheme Announced - 2018 Funding Allocated - $170.0 million (construction funding deferred)
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | TBD
2. Final Business case | 2018 | Mid-2022
3. Planning and Pre-Construction Activities | 2021 | TBD
4. Construction | TBD | TBD
Project Details - Cairns Water Security Program - Stage 1 Announced - 2022 Funding Allocated - $195 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2026
2. Final Business case | 2021 | Late 2022
3. Planning and Pre-Construction Activities | 2021 | 2024
4. Construction | 2024-07-01 | Mid-2026
Project Details - Big Rocks Weir Announced - 2018 Funding Allocated - $38.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | TBD
2. Final Business case | 2018 | 2020
3. Planning and Pre-Construction Activities | 2021 | TBD
4. Construction | TBD | TBD
Project Details - Mount Morgan Water Supply Announced - 2022 Funding Allocated - $30.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2021 | 2024
2. Final Business case | 2021 | Mid-2022
3. Planning and Pre-Construction Activities | Early 2022 | Late 2023
4. Construction | 2024-01-01 | Late 2025
Project Details - Groundwater Improvements in the Lower Burdekin Announced - 2022 Funding Allocated - $12.5 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | Early 2021 | 2026
2. Final Business case | 2019 | Mid 2022
3. Planning and Pre-Construction Activities | 2020 | 2024
4. Construction | 2025 | Late 2026
Project Details - Birdsville Water Security Announced - 2024 Funding Allocated - $2.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2024-07-01 | TBD
2. Final Business case | TBD | TBD
3. Planning and Pre-Construction Activities | TBD | TBD
4. Construction | Early 2025 | Late 2026
Completed Projects | Funding Provided | Completion Date
1. Mareeba-Dimbulah Water Supply Scheme | $11.6 million | 2021-12-01
2. Warwick Recycled Water Treatment Upgrade | $0.5 million | 2023-06-01
3. Rookwood Weir | $183.6 million | 2024-10-01
Western Australia Projects
Project Details - Busselton Water Supply Improvement Announced - 2024 Funding Allocated - $29.6 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | TBD | TBD
2. Final Business case | TBD | TBD
3. Planning and Pre-Construction Activities | Late 2024 | Mid-2026
4. Construction (incl. procurement and main construction) | Mid-2026 | Mid-2029
Project Details - Bunbury Water Resource Recovery Scheme Announced - 2024 Funding Allocated - $24.9 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | TBD | TBD
2. Final Business case | TBD | TBD
3. Planning and Pre-Construction Activities | Late 2024 | Early 2025
4. Construction | Mid-2025 | Late 2026
Project Details - Water Quality and Security for Guilderton Announced - 2024 Funding Allocated - $3.4 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | TBD | TBD
2. Final Business case | TBD | TBD
3. Planning and Pre-Construction Activities | TBD | TBD
4. Construction (incl. procurement and main construction) | Mid-2025 | Mid-2026
South Australia Projects
Completed Projects | Commencement Date | Completion Date
1. Northern Adelaide Irrigation Scheme | $37.6 million | 2019-09-01
Tasmanian Projects
Project Details - Greater South East Irrigation Scheme Announced - 2024 Funding Allocated - $150.1 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | TBD | TBD
2. Final Business case | 2021 | 2023-11-01
3. Planning and Pre-Construction Activities | TBD | TBD
4. Construction (incl. procurement and main construction) | TBD | TBD
Project Details - Northern Midlands Irrigation Scheme Announced - 2019 Funding Allocated - $109.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | 2024
2. Final Business case | 2020 | Late 2022
3. Planning and Pre-Construction Activities | 2020 | Mid-2023
4. Construction (incl. procurement and main construction) | 2024-09-01 | Late 2026
Project Details - Sassafras-Wesley Vale Irrigation Scheme Announced - 2019 Funding Allocated - $62.1 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2018 | Late 2023
2. Final Business case | 2020 | Late 2022
3. Planning and Pre-Construction Activities | Late 2023 | Early 2024
4. Construction (incl. procurement and main construction) | TBD | Late 2026
Project Details - Tamar Irrigation Scheme Announced - 2019 Funding Allocated - $16.4 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | 2019 | 2025
2. Final Business case | 2024 | 2025
3. Planning and Pre-Construction Activities | 2020 | TBD
4. Construction (incl. procurement and main construction) | TBD | TBD
Project Details - Bicheno Recycled Water Scheme Announced - 2022 Funding Allocated - $5.0 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | Late 2022 | Late 2023
2. Final Business case | 2021 | Late-2023
3. Planning and Pre-Construction Activities | 2022 | TBD
4. Construction (incl. procurement and main construction) | TBD | TBD
Completed Projects | Funding Provided | Completion Date
1. Scottsdale Irrigation Scheme | $25.3 million | 2020-11-01
2. Don Irrigation Scheme | $26.3 million | 2023-10-01
3. Lake Leake Dam Life Extension Upgrade | $1.5 million | 2024-07-01
Northern Territory Projects
Project Details - Darwin Region Water Supply Infrastructure Program (DRWSIP) - Stage 1 Announced - 2022 Funding Allocated - $300.6 million
DRWSIP - Manton Dam Return to Service | Commencement Date | Completion Date
1. Community and stakeholder engagement | N/A | N/A
2. Final Business case | 2018 | 2021
3. Planning and Pre-Construction Activities | 2018 | 2025
4. Construction (incl. procurement and main construction) | 2024-07-01 | Mid-2026
DRWSIP - Adelaide River Off-stream Water Storage Pre-Construction | Commencement Date | Completion Date
1. Community and stakeholder engagement | Early 2022 | 2024
2. Final Business case | 2018 | Late 2021
3. Planning and Pre-Construction Activities | Early 2022 | Late 2025
4. Construction (incl. procurement and main construction) | N/A | N/A
Project Details - Yulara Water Supply Announced - 2024 Funding Allocated - $13.2 million
Project Stage | Commencement Date | Completion Date
1. Community and stakeholder engagement | Mid-2024 | Late 2026
2. Final Business case | 2019 | Late 2024
3. Planning and Pre-Construction Activities | 2019 | Late 2024
4. Construction (incl. procurement and main construction) | Mid-2024 | Mid-2029
Connections Pathway Packages of Projects
Project Details - NSW Connections Pathway Package (3 projects) Announced - 2019 Funding Allocated - $10.5 million
Ongoing Projects | Commencement Date | Completion Date
1. Urbenville Water Supply Project | Early 2023 | Early 2025
Completed Projects
1. West Wyalong Water Reliability Project | Late 2022 | 2023-12-01
2. Walcha Off-Stream Water Storage | Late 2022 | 2024-09-01
Project Details - VIC Connections Pathway Package (9 projects) Announced - 2019 Funding Allocated - $20.0 million
Ongoing Projects | Commencement Date | Completion Date
1. Victoria’s Emergency Water Supply Point Network | Mid-2022 | Early 2025
2. Sunday Creek Irrigation and Reconfiguration project | Late 2022 | Early 2025
Completed Projects
1. Kyneton Recycled Water Irrigation project | Mid-2022 | 2023-03-01
2. Gisborne to Sunbury Recycled Water Interconnector:Stage 1 | Mid-2022 | 2023-04-01
3. Bacchus Marsh Resilience and Critical Infrastructure | Mid-2022 | 2023-08-01
4. Macalister Resilience and Critical Infrastructure | Mid-2022 | 2023-08-01
5. Goulburn-Murray Irrigation District Channel Embankment Infrastructure Improvement project | Early 2022 | 2023-09-01
6. Sunday Creek Irrigation and Reconfiguration project | Late 2022 | 2024-09-01
7. Critical Headworks Infrastructure for the Modernised Goulburn-Murray Irrigation District | Early 2022 | 2024-12-01
Project Details - QLD Connections Pathway Package (1 project) Announced - 2021 Funding Allocated - $4.8 million
Completed Project | Commencement Date | Completion Date
1. Warrens Gully System Capacity Upgrade | Mid-2021 | 2024-02-01
Project Details - WA Connections Pathway Package (9 projects) Announced - 2021 Funding Allocated - $20.0 million
Completed Projects | Commencement Date | Completion Date
1. Agricultural Area Dams and Strategic Community Water Supplies | Late 2021 | 2024-07-01
2. Community Water Supplies Partnership Program with Local Government | Late 2021 | 2024-07-01
3. Cave Springs Road Tail Water Return System | Late 2021 | Mid-2023
4. Jerramungup Dam Catchment Improvement | Early 2023 | Mid-2023
5. Cranbrook Dam Catchment Improvement | Early 2023 | Mid-2023
6. Ravensthorpe Dam Catchment Extension | Late 2023 | Late 2023
7. Katanning to Kojonup Pipeline Enhancement | Mid-2023 | Late 2023
8. Wongutha Independent Water Security Pilot | Late 2021 | Early 2024
9. Gascoyne Irrigation Scheme Augmentation and Modernisation | Mid-2022 | Mid-2024
Project Details - SA Connections Pathway Package (7 projects) Announced - 2021 Funding Allocated - $14.1 million
Ongoing Projects | Commencement Date | Completion Date
1. Barossa Wine Grape Water Source Diversification | Early 2023 | Early 2025
2. Improving Water Deliverability and Accessibility in the Lower Murray Reclaimed Irrigation Area | Late 2023 | Early 2025
Completed Projects
1. Regional Recharge Farms | Mid-2022 | Mid-2023
2. Porgona Barbata - Water for High-Tech Horticulture | Late 2023 | Mid-2023
3. Greenways Irrigation Trust - Increasing water availability, reliability, and efficiency | Mid 2022 | Late 2023
4. Waikerie Irrigated Agricultural Water Access and Security project | Mid-2023 | Mid-2024
5. Recycled Water Pipeline to Nairne - Stage 1 | Mid-2023 | Late 2024
Project Details - TAS Connections Pathway Package (4 projects) Announced - 2021 Funding Allocated - $20.0 million
Ongoing Projects | Commencement Date | Completion Date
1. South Arm Recycled Water Pipeline | Mid-2022 | Late 2025
2. Shellfish Lease Water Quality Improvement Program | Early 2023 | Early 2025
Completed Projects
1. Penna Recycled Water Scheme Expansion | Mid-2023 | Early 2024
2. Greater Meander Irrigation Scheme | Late 2022 | 2024-11-01
Project Details - NT Connections Pathway Package (2 projects) Announced - 2021 Funding Allocated - $7.4 million
Ongoing Projects | Commencement Date | Completion Date
1. Katherine Logistics and Agribusiness Hub Water Supply Project | Mid-2022 | Mid-2026
2. Emerging Agribusiness Precinct - Gunn Point Peninsula | Early 2024 | Mid-2026
Water Infrastructure for Sustainable and Efficient Regions (WISER) Packages of Projects
Project Details - QLD WISER Package (5 projects) Announced - 2024 Funding Allocated - $20.0 million
Projects | Commencement Date | Completion Date
1. Mossman River Intake | Early 2025 | Late 2027
2. Cassowary Coast Leak Reduction | Late 2024 | Mid-2025
3. Longreach Water Security for Growth | TBD | Mid-2027
4. Mareeba Regional Water Security | Early 2025 | Mid-2027
5. Central Highlands Drinking Water Supply Program | TBD | Mid-2027
Project Details - WA WISER Package (5 projects) Announced - 2024 Funding Allocated - $20.0 million
Projects | Commencement Date | Completion Date
1. Community Water Supplies Partnership Program with Local Government | Mid-2025 | Mid-2027
2. Jurien Bay Water Security Upgrade | Mid-2025 | Early 2026
3. Esperance Water Security Upgrade | Early 2025 | Late 2025
4. Agricultural Area Dams and Strategic Community Water Supplies | Mid-2025 | Mid-2027
5. Albany Water Security Upgrade | Mid-2025 | Mid-2026
Project Details - SA WISER Package (4 projects) Announced - 2024 Funding Allocated - $6.6 million
Projects | Commencement Date | Completion Date
1. NAIS Recycled Water Pipeline to Mallala | Mid-2025 | Mid-2026
2. Waikerie Wastewater Treatment Plant Upgrade | Mid-2025 | Mid-2027
3. Loxton Wastewater Treatment Plant Upgrade | Mid-2025 | Mid-2027
4. Wellington East Water Supply | Mid-2025 | Mid-2027
Project Details - Tas WISER Package (4 projects) Announced - 2025 Funding Allocated - $20.0 million
Projects | Commencement Date | Completion Date
1. Bothwell Water Treatment Plant Replacement | 2025 | 2027
2. Ellendale Water Supply Pipeline | 2025 | 2026
3. Oatlands Water Treatment Plant Replacement | 2025 | 2026
4. Cambridge-Clarence Recycled Water Interconnector | 2025 | 2027
First Nations Projects
Project Details - NSW - Far West Water Treatment Plants Announced - 2024 Funding Allocated - $10.0 million
Commencement Date | Mid-2024
Completion Date | Late 2025
Project Details - NSW - Lightning Ridge Bore Water Pipeline Announced - 2024 Funding Allocated - $1.3 million
Commencement Date | Mid-2025
Completion Date | Late 2025
Project Details - QLD - Cherbourg Water Quality Improvement Project Announced - 2024 Funding Allocated - $12.8 million
Commencement Date | Mid-2025
Completion Date | Late 2026
Project Details - QLD - Northern Peninsula Area Water Supply Project Announced - 2024 Funding Allocated - $5.0 million
Commencement Date | Late 2024
Completion Date | Late 2025
Project Details - QLD - Doomadgee water supply project phase 1 Announced - 2024 Funding Allocated - $4.5 million
Commencement Date | Late 2024
Completion Date | Late 2025
Project Details - QLD - Mornington Island water supply stage 1 Announced - 2024 Funding Allocated - $3.0 million
Commencement Date | Early 2025
Completion Date | Late 2025
Project Details - QLD - Wujal Wujal water infrastructure upgrades Announced - 2024 Funding Allocated - $3.0 million
Commencement Date | Late 2024
Completion Date | Late 2025
Project Details - QLD - Dajarra water security project stage 1 Announced - 2024 Funding Allocated - $0.97 million
Commencement Date | Late 2024
Completion Date | Mid-2025
Project Details - WA - Treatment, Storage and Pumping Mini Plant Program – Phase 1 Announced - 2024 Funding Allocated - $3.8 million
Commencement Date | Mid-2025
Completion Date | Late 2027
Project Details - WA - Water Pipework Replacement Program - Phase 1 Announced - 2024 Funding Allocated - $3.0 million
Commencement Date | Late 2025
Completion Date | Late 2027
Project Details - WA - Chlorination of Water Supply - Phase 1 Announced - 2024 Funding Allocated - $3.0 million
Commencement Date | Mid-2025
Completion Date | Late 2027
Project Details - WA - Bore Pipe Upgrade Program - Phase 1 Announced - 2024 Funding Allocated - $2.6 million
Commencement Date | Mid-2025
Completion Date | Mid-2027
Project Details - WA - Bore Sealing Program - Phase 1 Announced - 2024 Funding Allocated - $2.3 million
Commencement Date | Mid-2025
Completion Date | Mid-2027
Project Details - WA - Water Security for the Lundja Aboriginal Community Announced - 2024 Funding Allocated - $0.9 million
Commencement Date | Late 2024
Completion Date | Mid-2025
Project Details - WA - Water Security for the Bondini Aboriginal Community Announced - 2024 Funding Allocated - $0.8 million
Commencement Date | Late 2024
Completion Date | Mid-2027
Project Details - SA - Iga Warta Water Security Announced - 2024 Funding Allocated - $0.2 million
Commencement Date | Mid-2024
Completion Date | Late 2024
Project Details - NT - Better Bores for Communities Phase 1 (10 projects) Announced - 2024 Funding Allocated - $27.8 million
Commencement Date | Mid- to Late 2025
Completion Date | Late 2026
Project Details - NT - Maningrida Water Supply Upgrade (3 projects) Announced - 2024 Funding Allocated - $13.0 million
Commencement Date | Mid-2025
Completion Date | Late 2026
Project Details - NT - Yuendumu Water Security and Supply Strategy (3 projects) Announced - 2023 Funding Allocated - $11.1 million
Commencement Date | Late 2023
Completion Date | Early 2025
Project Details - NT - Milingimbi Water Security Strategy (3 projects) Announced - 2023 Funding Allocated - $6.4 million
Commencement Date | Late 2023
Completion Date | Early 2025
Project Details - NT - Gove Peninsula Water Supply Upgrade Strategy (2 projects) Announced - Funding Allocated - $
Announced - 2024 Funding Allocated - $5.4 million
Commencement Date | Early 2025
Completion Date | Late 2025
Project Details - NT - Numbulwar Water Security Strategy - Phase 1 (3 projects) Announced - 2024 Funding Allocated - $
Announced - 2024 Funding Allocated - $1.8 million
Commencement Date | Mid-2024
Completion Date | Early 2025
*Note there are no projects currently underway in the Australian Capital Territory.